## ProjectTaskList
| Project Start |  | 2020-02-26
CUSTOMISATION WORKS INTEGRATION WITH 3CX IP-PBX | OWNER | PRIORITY | START | END | % COMPLETE | NOTES
Call Reports Customisation Module
Service Level per interval (15, 30, Hourly) | Call Center | HIGH |  |  | 0%
Agents KPI per interval as well as overall | Call Center |  |  |  | 0%
Logins and logouts per agents and their status | Call Center | HIGH |  |  | 0% | Agents Released Calls
Logins and logouts per agents and their status | Call Center | HIGH |  |  | 0%
Any other logged data should be enabled for exportation to CSV or Database interface | Call Center |  |  |  | 50%
Wallboard Customisation Module
Ability to reflect monitoring in real-time monitoring of (defined) service levels and agents statistics | Call Center |  |  |  | 0%
Ability to change the status (definitions) of agents aux, breaks, etc... | Call Center | HIGH |  |  | 0%
Web Interface Module
Inclusion of the realtime data of SL, Agents, on-going calls | Call Center | HIGH |  |  | 20%
Ability to search for the telephone numbers of recorded calls | Call Center |  |  |  | 0%
Management of queues, agents, and reports generation | Call Center |  |  |  | 0%
Ability to self-manage texts to be sent to customers waiting for on-hold | Call Center |  |  |  | 0%
History of calls should allow for the download of bulk recordings | Call Center |  |  |  | 0%
CRM Integration Module 3
Ability to connect to our customer database to fetch all data internally | Call Center |  |  |  | 0%
All customers data should be exported to the agent's interface to show orders history upon the agent picking up of calls | Call Center |  |  |  | 0%
Ability to self-service call 3CX's CallFlow | Call Center |  |  |  | 0%
SMS Interface Module
Integrate with SMS providers | Call Center |  |  |  | 0%
Separate text messages can be assigned to different queues (e.g. Customer waiting on-line for more than a minute are sent a message to use our website channels) | Call Center |  |  |  | 0%
SMS texts can be assigned to any queue or action to customers (e.g. Callbacks) | Call Center |  |  |  | 0%
(Exclude SMS Gateway & SMS Subscription) | Call Center |  |  |  | 0%
Social Media Integration Module
WhatsApp account setup and integration | Call Center |  |  |  | 0%
Agents and Supervisors web interface should allow for interaction with customers' WhatsApp messages | Call Center |  |  |  | 0%
Integrate Facebook messenger | Call Center |  |  |  | 0%
Webchat for our website and apps integration | Call Center |  |  |  | 0%